# ORGANIZATION FOR MANAGEMENT,  PROFIT, AND  EXPENSE CONTROL

Last week during the survey process and our conversations this week, we have discussed your “needs” and “wants” for you and your business. And, we’ve reviewed what we can accomplish by achieving your business goals and objectives. The business results will help you attain your personal goals as well.

# You have expressed your wish to establish or restructure your business through a more defined organization and strategy, implementing controlled financial business practices.  By developing and implementing a well-defined operational and financial structure, you will be able to move your business from where you are today to where you want to be.

# Implementing a strategic plan will enable you to align your company for greater profitability and ease of operation. You will reap the benefits of having the appropriate operative infrastructure in place. Feel a positive difference as you develop and implement accountability.

# PROJECT OBJECTIVES FOR ORGANIZATION OF MANAGEMENT

It is only within a functionally sound organizational business structure that Your Company can create the desired future.  To that end, our first step is to design a functional organizational chart that clearly defines the lines of authority, roles, and responsibilities for all personnel. A clear understanding of these points allows us to notice gaps and redundancies and analyze “team members” and qualified professionals and their roles within Your Company.

ACTION 1.1 – To understand your total operation, it is essential to investigate, review, discuss, and assess the reports, operations, controls, policies, and procedures. We will evaluate employee capabilities and utilization of key personnel at Your company. This process is necessary to determine the organizational structure and understand the information and communication flow, reporting relationships, duties, problems, bottlenecks, and improvement possibilities.

OBJECTIVE 1.1 – This will provide the opportunity and forum to become thoroughly familiar with the current situation and develop the appropriate strategy to recommend and implement the necessary adjustments and improvements to your company’s structure by identifying the areas in need of connection, linking or modification.

# ACTION 1.2 – Work with ________ to establish a strategic plan to separate Your Company’s back office and HR functions from Your Company and either find other back-office support vendors and/or bring them inhouse.

# OBJECTIVE 1.2 – Implement a strategy to extricate your company's financial and HR functions from your company while retaining the domain name of yourcompany.com.

# ACTION 1.3 – Evaluate accounting data, doing a forensic analysis of the allocation of charges related to commingled monies or accounts.

# OBJECTIVE 1.3 –Determine the extent of any possible improprieties or excessive allocation to Your Company by Your Company. Who has been handling all of the back-office functions?

# ACTION 1.4 – Conduct interviews with all of Your Company’s support personnel and determine skills related to their associated job functions through questions.

# OBJECTIVE 1.4 –To conduct a personality audit related to the position requirements Vs. the best suitable position for their skill set.

# ACTION 1.5 – Develop a functional organizational structure for each company to facilitate timely decision-making by leadership/management and communication flow.

# OBJECTIVE 1.5 – A streamlined process that will assist on-site management in making effective decisions based on their defined functional roles; while meeting Your Company’s business requirements.

# ACTION 1.6 – Develop performance-based job descriptions with supporting performance criteria standards for the primary positions identified on the organization chart.

# OBJECTIVE 1.6 –To assure that the organization's managers or major function holders understand their duties, authorities, and responsibility of their defined functional roles. Ensuring that you meet Your Company’s business requirements through performance-based criteria required of the position.

# ACTION 1.7 – Working with _______, develop an employee evaluation system for all position levels incorporating the self-improvement methodologies that are encouraged.

# OBJECTIVE 1.7 –This will give structure to improve all employees' performance and a key part of any incentive to be awarded.

# ACTION 1.8 - Conduct Management training sessions for key employees to instruct on “best problem resolution strategy for conflict issues,” in addition to understanding methods for controlling cost.

# OBJECTIVE 1.8 – Work with key employees to improve their understanding of their

# roles as they relate to one another and improve their communication within the company structure.

ACTION 1.9 – Review existing employee policies and evaluate the employee handbook to determine if it is current with company HR policies.

# OBJECTIVE 1.9 – This will standardize the understanding of the company’s position on emergency procedures, drug policy, vacations, insurance, etc.

ACTION 1.10 – Evaluate the current strategic business plans and work with the owners. Put into place a 1, 3, and 5-year business plan for Your Company.

# OBJECTIVE 1.10 – To plan for the business requirements, focusing on profitability incorporating adjustments for changes and planning for capital expenditures, rather than living in the past through last year’s accounting statements. To provide a set of goalposts to evaluate company performance and monitor the success of Your Company.

ACTION 1.11 – Develop a “Management Leadership Team” made up of Key employees within the different companies and the functional areas of sales, financial, IT production, etc.

# OBJECTIVE 1.11 – These are the key operations and finance personnel that

# will be the company's future. They will work as a team to meet strategic and tactical challenges of the company and improve their ability to function.

# PROJECT OBJECTIVES FOR-PROFIT AND EXPENSE CONTROL

# We'll look at several issues to structure financials and equip the company to move to its next level of revenue growth, profitability, and strong cash flow.  Consequently, this area of consulting engagement will have the following main areas:

ACTION 2.1 – Review existing work process flows in the order process through billing functions. We will chart and then identify areas of concern that are inefficient or redundant. We’ll establish systems to facilitate an in-house, back-office operation.

OBJECTIVE 2.1 – To eliminate congestion, redundancy, and other problems that result in late billing, failure to bill, and other administrative processes that fall through the cracks. We’ll ensure that all financial and HR functions are brought in-house.

ACTION 2.2 – Review, discuss, and assess the current financial reports, working with _______________ to complete a line-by-line evaluation of the company’s fixed and variable costs.  Review the existing system of recording transactions to ensure the proper allocations. Revise and make the necessary changes in the chart of accounts to categorize the costs based on their relationship and variations to revenue.  Work with ___________ in the development of an annual fiscal budget, and to consider preplanned profit as a fixed-line item of expense.

OBJECTIVE 2.2 – Revising the Chart of Accounts to ensure better financial management information and developing a budget and forecast will result in greater profitability.  The recording of the transactions will be standard and accurate. Your Company will have a fiscal budget to guide its operation via a flexible monthly budget. We will observe actual variances, and key personnel can take timely action.  Profit will be preplanned rather than “hoped for.”  Timely planning, evaluation, and action will secure positive results for your company.

ACTION 2.3 – Based on the projected Annual Budget, establish how to utilize the Projected Revenue, Project Costs (variable costs), and General and Administrative Expenses (fixed costs) to determine the company’s Break-Even Point and the Overhead Percentage.

OBJECTIVE 2.3 – Management will have the ability to utilize Break-Even Point and Overhead Percentage in pricing their decision-making processes.  Once the Beak-Even Point and Overhead Percentage have been determined, it will be relatively easy to estimate the sales volume that would be necessary to produce the desired results.  This can result in a competitive advantage and allow you to predict the results of your potential business decisions.

ACTION 2.4 – Develop a monthly budget incorporating betas and step costs as needed. Build into the budget a monthly variance report that will measure your forecasted monthly budget against your actual outcome—at the same time, understanding the relationship between increases in sales and increased direct costs.

OBJECTIVE 2.4 – Establish profit as the first line item of expense and have it preplanned to assure that profit is not a residual item. This prevents the failure to incorporate profit as a part of the operational expense and not have the necessary accountability to assure that the company remains profitable.

ACTION 2.5 – Work with _____________ to develop “Dashboard” reports including job status reporting and bid status, a 6-week cash flow report, accounts receivable collection forecasting, accounts payable payment scheduling.

OBJECTIVE 2.5 – This will be useful as a guide to plan expenditures, capital improvements, and forecast revenue, and workforce requirements.

ACTION 2.6 –Review present incentive plan; discuss alternatives and improvements to provide guidelines for awarding bonuses to individuals based upon their contribution to Your Company's profitability.

OBJECTIVE 2.6 – This assures that the employees who make the greatest contribution to company profitability receive the largest reward or recognition. This process will incentivize those employees who will be the most instrumental in making field command decisions that will improve company profitability.

PROJECT OBJECTIVES FOR -SALES AND MARKETING

For the company to meet sales forecasts and maintain adherence with the Strategic Plan's short- and long-term elements, it needs to be economically productive for Your Company.

# ACTION 3.1 – Review the sales compensation program and evaluate the salary and commission component.  Make sure it has milestones and a gradual percentage balance that becomes more commission rather than salary over a fixed period.

# OBJECTIVE 3.1 – To incentivize the new sales personnel to pursue new customers and new markets for Your Company.

# ACTION 3.2 – Review the sales expense related to the separate companies and work with ______________ to develop a sales expense budget for travel and marketing.

# OBJECTIVE 3.2 – To control the indirect costs associated with sales by having a set travel plan and identify the areas most influential in garnering new sales or customers.

PROJECT OBJECTIVES FOR PRODUCTION PLANNING

# ACTION 4.1 – Review existing production floor operation Vs. having a production plan to adhere to for the different product lines. Work with Joe and Eric to develop a process flow chart.

# OBJECTIVE 4.1 – To identify areas that may bottleneck the process flows and correct to increase production.

PROJECT DOCUMENTATION AND EMPLOYEE INDOCTRINATION

ACTION 5.1 – Train all personnel in the new systems and procedures related to that individuals’ function within the organization.

OBJECTIVE 5.1 – To provide a complete understanding by each individual of their duties, responsibilities, authority, reporting relationship within the new functions of the organization.

ACTION 5.2 – Prepare the Operating Procedures, outlining and explaining the preparation and use of all reports, forms, methods, and systems developed during each assignment phase. Organize this information and all project documentation into a Master Binder and a flash drive.

OBJECTIVE 5.2 – Provides a permanent archive of all work for future reference and/or training. All procedures, documentation, and spreadsheets will be prepared using Microsoft Office and copied electronically.

The preceding action points comprise the Project Plan. They will be completely developed and implemented within 500 hours ± 10% as agreed upon in the Consulting Service Agreement DATE.

This is the Project Plan described in the "Working Agreement for Consulting Services," between YOUR COMPANY and Belfield Management Solutions (BMS).  This project plan is an evolving document, AKA a working document that will be adaptive to your business and personal wants and needs.  During the project, we may also present you with suggestions and/or recommendations concerning other areas of your business, which need attention but are not addressed in the Project Plan.  However, these will not be developed without your full approval, separate and apart from this Project Plan.  By developing and installing the above program points, Your company’s operational and/or fiscal challenges will be reduced significantly. This will provide you the opportunity to focus your

energy and talents to expand and enhance your business.  The success of this project is determined by your commitment to the process as the leader of Your Company and to capitalize on the company’s strengths for long-term gradual growth, built on solid operational management.

Submitted by:					Examined and Approved by:

____________________      	 ___________________  	__________________

Consultant Name			 Eric Jones			Joe Jones

CBS LLC.			 	 ABC CO.			ABC CO.

Senior Project Manager		 Owner			Owner

10/24/2019				 10/24/2019			10/24/2019