## Sheet1
Please refer to 4-SEC – 67D97DB Design specification sheet
0
| crane 4500/.6 est) | materials | labor |  |  | 1PH9579B – The Condo Shop
| 8166.6667 |  |  | 8166.6667 | Crane Phila Street and Escort
|  |  | 4800 | 4800 | RF SATURDAY Load |  time and a half 3200*1.5= 4800 - GC will pick up materials at CTDI is Swedesboro
|  |  | 1200 | 1200 | Depoy / BOM included | o GC to include (2) material pickups and (1) material drop off
|  |  | 38400 | 38400 | RF | RF (4 days hybrid, 4 days antennas/rru, 2 days cabinet= 10 days, plus 2 days intergration), rooftop with four (4) man crew, structural excluded, excluded civil, electrical exculded, materials excluded
|  | 1566.6667 |  | 1566.6667 | RF included |  Materials, Supports, each sector 235/.6=$391.67*4= GC to install (2) antennas, (1) 4449 radio unit, (10) fiber jumpers, (4) coax jumpers per sector
|  | 2000 |  | 2000 | RF included |  Supports, grounding cable tray =60*8*2.5/.6= GC to install (4) hybrid cables
|  | 240 |  | 240 | RF included | o =4*2*18/0.6= $240.00, GC will need to supply and install power extenders and fibers as needed.
|  |  |  | 0 | RF included | o Please plan on performing pre and post fiber testing
|  |  |  | 0 | RF included | o Please plan on cleaning all SFP optical ports and all fiber connections
|  | 1176.4667 |  | 1176.4667 | RF included |  materials 500' #2 Green/#2 Tinned GC to supply and install all grounding and equipment as needed as per cd’s
|  | 0 | 0 | 0 | Structural Included |  (Structural 3 days, 8500 est on steel to site) GC to supply and install all steel dunnage for antenna mounting as per cd’s / SA
|  | 16264.534 | 9600 | 25864.534 | RF included |  Sitepro1 @ 139.49, 6% tax, 10% = shipping cost, per 8', 60 sections =GC labor 3 days four man crew @ 3200=9,600 - to supply and install covered cable tray on sleepers as needed for hybrid runs
|  | 583.3333 | 1600 | 2183.3333 | RF included |  $200 materials, 150 ports/.6 mu=583.33 , 2 men one dayGC to supply and install entry port for hybrid lines as per cd’s
|  | 28520.8333 | 28520.8333 | 57041.6667 | Elec Included |  GC to install PPC panel, Emerson, sub meter on wall as per cd’s
|  |  |  | 0 | Elec Included- see lighting -add on |  GC will supply and install (2) dual 100 Watt lights on the penthouse roofs as discussed or in the attached
|  |  |  | 0 | Elec Included |  1440 per two man plus 20% m/u, est 250 for lighting and cercuitsGC will supply and install new cold start lighting in the room above our BTS cabinet
|  |  |  | 0 | Roofer see OSHA - AOS |  GC will supply and install walking pads from the penthouse over to the TMO equipment room
|  |  |  | 0 | RF included |  GC to install (1) BTS cabinet
|  |  |  | 0 | RF included | o GC will build out cabinet as per design spec sheet
|  | 150 |  | 150 | RF included | o Electrcian - 150 miscenaious materials, install batt, delivered to site by Cci) Batteries, sub rack, SPDs, plates, radios, routers, etc Please make sure that everything is labeled inside of
|  |  |  | 0 |  | the BTS cabinet
|  | 0 |  | 0 | Elec Included | o Extend -48 DC feed from the BTS cabinet to the Emerson cabinet
|  | 0 |  | 0 | Elec Included | o Supply and install 6 strand single mode LC to LC fiber jumper
|  | 132.5 |  | 132.5 | RF included |  five (5) locks =5*15*1.06/0.6 GC to supply and install locks on TMO equipment | 162.657
|  |  |  | 0 | RF included |  GC to label equipment with site ID and carrier information
|  |  |  | 0 | Elec Included |  GC to supply and install inner duct , conduit, etc w/ a pull string from our Emerson cabinet to the basement (following
|  |  |  | 0 |  | the existing patch of the grounding and existing fiber run)
|  | 0 | 0 | 0 | Elec Included |  (APU rooftop scope / 9500) GC to install APU and perform startup
|  |  |  | 0 |  | o GC to supply 1” conduit from APU to BTS w/ CAT 6 cable for alarm block
|  |  |  | 0 |  | o GC to supply 2” conduit from APU to BTS for power cables |  | 12.6667
|  |  |  | 0 |  | o GC to supply 3/4” conduit from APU to NG D-Mark
|  |  |  | 0 | Elec Included |  GC will need to supply a sub meter
|  | 1050 | 1600 | 2650 | civil |  Gate $450, 2 corner post, midrail, top rail, fabric, grounding,600, labor 1 day and GC to supply and install fencing in the penthouse
|  |  |  | 0 | RF included |  GC to be onsite during integration, please plan on having 2 trips in your quote
|  | 1272 |  | 1272 | MGT Exp- Parking and Travel | Parking $763.20, =$60*12/0.6= $1,272.00 cost with /markup
|  |  |  | 0 | Electrical Inc- OSHA - AOS | lighting and 1/2" RGS and 120LF 3way switch $1,000 labor and materials
|  | 2120 | 1766.6667 | 3886.6667 | Roofer (OSHA) | Walking Pads, 120 LF 55 each every 3LF, (materials 30, labor 25=55*120/3/.6
|  | 1250 | 2000 | 3250 | Roofer | Roofer, 1,250 pitch pockets, labor 1,200 with .6 mu $2,000
|  | 8333.3333 | 9600 | 17933.3333 | Structural | Steel , Steel Dunnage and sector mounts, est 5,500/.6- includes Hilti HY-70, delivery to site labor for install by Cci 3 days, 3200*3
|  | 3333.3333 | 3166.6667 | 6500 | Plumber Gas Meter | Plumber /License and Gas Meter
|  |  | 2250 | 2250 | Tax- City of Philadelphia | Philadelphia Labor Tax 7.5%
|  | 1225 | 0 | 1225 | Permits | GC Permits, 450+300 Final Inspection Walk, Plumbing Permit and Inspecuton 450
|  |  |  | 0 | Elec Included | Electrical Permits and Inspection
|  | 1061.1667 |  | 1061.1667 | Turnover Documention | Closout Package - Level 3 $450/.6with two (2) permits= 175/.6
| 8166.6667 | 70279.1673 | 104504.1667 | 182950.0007
Est Gross | Est COGS
31085.4003 | 46628.1004 | 42.48% | 77713.5007 | 55600 | RF Labor | 55600
40% | 60% |  |  | 22113.5007 | RF Materials
7173.3333 | 10760 | 9.802% | 17933.3333 | 9600 | Structural Labor
40% | 60% |  |  | 8333.3333 | Structural Materials
22816.6667 | 34225 | 31.18% | 57041.6667 | 28520.8333 | Electrical
40% | 60% |  |  | 28520.8333 | Electrical Materials
2854.6667 | 4282 | 3.901% | 7136.6667 | 3766.6667 | Roofer Labor
40% | 60% |  |  | 3370 | Roofer Materials
2600 | 3900 | 3.553% | 6500 | 3166.6667 | Plumber
40% | 60% |  |  | 3333.3333 | Plumber Materials
3266.6667 | 4900 | 4.464% | 8166.6667 | 8166.6667 | Crane
40% | 60% |  |  | 0 | City of Phila Police Escort/Saturday
1060 | 1590 | 1.448% | 2650 | 1600 | Civil Labor
40% | 60% |  |  | 1050 | Civil Materials
900 | 1350 | 1.23% | 2250 | 2250 | City of Phila Tax
40% | 60% |  |  | 0
1423.2667 | 2134.9 | 1.945% | 3558.1667 |  | Management Labor
40% | 60% |  |  | 3558.1667 | Management Materials | COP , Travel
73180.0003 | 109770.0004 | 100% | 182950.0007 | 182950.0007
40% | 60%
|  |  | 186683.6741 | PLUS 2% | offset early pay discount?
|  |  | 3733.6735 |  | 3734
|  |  | 184797.9805 | PLUS 1%
|  |  |  | 189950 | ebid